## Sheet1
Software Design Plan For Perpetual Accelerated Motion Game |  |  | Dec 13 to Dec 20
|  |  | F | S | S | M | T | W | T | F
Activity | Who | Duration
Design
Plan out architecture | Amanda | 2 h
Plan out collision math | Amanda | 4 h
Draw maps | Amanda | 1 h
Write out strings | Amanda | 1 h
Create Gantt Chart | Amanda | 2 h
Implementation
Create Abstract and Inherited Classes | Amanda | 2h
Create Ball, Wall, Rect Object Collision Logic | Amanda | 4h
Create Navigation Panes | Amanda | 3h
Create Circular Object Collision Logic | Amanda | 2h
Full Implemenation | Amanda | 1h
Document All Code | Amanda | 3h
Improve Design | Amanda | 2h
Testing
Test Collision Math | Amanda | 2h
Test Implemenation | Amanda | 2h
Documentation
Write out abstract documentation | Amanda | 1h
Write out code documentation | Amanda | 2h
Milestones
Wall and single map collision Proof Of Concept | Amanda | NA
Circular Obstacle Collision POC | Amanda | NA
Full Implemenation: Simple Design No Documentation | Amanda | NA
Full Implemenation: Completed Design, Documenation | Amanda | NA